## Table of Contents
Table of Contents
Artifacts
Business Case
Project Brief
Project Charter
Project Scope Statement
Project Vision Statement
Stakeholder Register
Assumption Log
Risk Register
Work Breakdown Structure
Project Schedule
Gannt Chart

## Metrics
Metrics Dashboard
| Task Completed | Task Remaining | Number of WBS Task | Number of Risks | Number of Requirements
| 83.84% | 16.16% | 99 | 13 | 21
|  |  | % of WBS Task Completed | Number of Assumptions | % of Requirements Completed
|  |  | 83.84% | 14 | 95.24%
Number of Stakeholders
5
| Requirements Completed | Requirements Remaining
| 95.24% | 4.762%

## Artifacts
Back to Table of Contents
PM Artifacts
Strategy Artifacts
| Deliverables | Description | Phase | Checklist | Document Link
| Business Case | A business case is a value proposition for proposed project that may include financial and non financial benefit | Initiation | TRUE | Project Charter
| Project Brief | A project brief provides a high level overview of the goals, deliverables, and process for the project | Initiation | TRUE | Project Charter
| Project Charter | A project charter is a document issued by the project initiator or sponsor that formally authorizes the existence of a project and provides the project manager with the wuthority to apply organizational resources to project activities. | Initiation | TRUE | Project Charter
| Project Scope Statement | This statement is is a component of the project or program management plan that describes how the scope will be defined. | Initiation | TRUE | Project Scope Statement
| Project Vision Statement | This document is a concise, high-level description of the project that states the purpose, and inspires the project team to contribute to the project. | Initiation | TRUE | Project Charter
Logs and Registers
| Deliverables | Description | Phase | Checklist | Document Link
| Stakeholder Register | A stakeholder register records information about project stakeholders, which includes assessment and classification of project stakeholders. | Initiation/Planning | TRUE | Stakeholder Register
| Assumption Log | An Assumption Log is a factor that is considered to be true, real, or certain, without proof or demonstration. A constraint is a factor that limits the options for managing a project, program, portfolio, or process. An assumption log records all assumptions and constraint throughout project management. | Planning | TRUE | Assumption Log
| Risk Register | A risk register is a repository in which outputs of risk management processes are recorded. Information in a risk register can include the person responsible for managing the risk, probability, impact, risk score, planned risk responses, and other information used to get a high-level understanding of individual risk | Planning | TRUE | Risk Register
| Requirements | This is a log that tracks all the requirements within a project | Planning | TRUE | Requirements
Hierarchy Charts
| Deliverables | Description | Phase | Checklist | Document Link
| Work Breakdown Structure | This chart is a hierarchical representation of the project organization, which illustrates the relationship between project activities and the organizational unites that will perform those activities. | Planning | TRUE | WBS
Baselines
| Deliverables | Description | Phase | Checklist | Document Link
| Project Schedule | A project schedule is an output of a schedule model that presents linked activities with planned dates, durations, milestone, and resources. | Planning | TRUE | WBS
Visual Data and Information
| Deliverables | Description | Phase | Checklist | Document Link
| Gannt Chart | This bar chart provides schedule information where activities are listed on the vertical axis, dates are shown on the horizontal axis, and activity durations are shown as horizontal bars placed according to start and finish dates. | Planning | TRUE | WBS

## WBS & Schedule & Gantt
Back to Table of Contents
| WBS Structure | [6 empty] | Project Schedule |  |  |  | Gantt Chart
[12 empty] | Color Key |  |  | = | Critical Path
[15 empty] | = | Non Critical Path
[12 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3
| Level | Sublevel | WBS Number | Task Owner | Critical Path (Yes, No) | Task Title | Description | Duration (Days) | Start Date | End Date | % of Task Complete | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26
[12 empty] | M | T | W | TR | F | S | SU | M | T | W | TR | F | S | SU | M | T | W | TR | F | S | SU
| 1 | 0 | 1 |  |  | Project Management | All PM Activities
| 1 | 1 | 1.1 |  |  | Initiation Phase | Project Kick Off Activities |  |  |  |  | 2025-10-25: Project End Date
| 1 | 1 | 1.1.1 | Dustin Carstens | Yes | Develop Project Charter |  | 1 | 2025-10-06 | 2025-10-07 | 100 | bar: 2025-10-06 to 2025-10-07
| 1 | 1 | 1.1.2 | Dustin Carstens | Yes | Identify Stakeholder |  | 1 | 2025-10-06 | 2025-10-07 | 100 | bar: 2025-10-06 to 2025-10-07
| 1 | 2 | 1.2 |  |  | Planning Phase | Planning Phase Activities
| 1 | 2 | 1.2.1 | Dustin Carstens | Yes | Create Stakeholder Register |  | 1 | 2025-10-06 | 2025-10-07 | 100 | bar: 2025-10-06 to 2025-10-07
| 1 | 2 | 1.2.2 | Dustin Carstens | Yes | Develop Assumption Log |  | 1 | 2025-10-06 | 2025-10-07 | 100 | bar: 2025-10-06 to 2025-10-07
| 1 | 2 | 1.2.3 | Dustin Carstens | Yes | Develop Risk Register |  | 1 | 2025-10-06 | 2025-10-07 | 100 | bar: 2025-10-06 to 2025-10-07
| 1 | 2 | 1.2.4 | Dustin Carstens | Yes | Create Work Breakdown Structure |  | 1 | 2025-10-07 | 2025-10-08 | 100
| 1 | 2 | 1.2.5 | Dustin Carstens | Yes | Develop Project Schedule |  | 1 | 2025-10-07 | 2025-10-08 | 100 | bar: 2025-10-07 to 2025-10-08
| 1 | 2 | 1.2.6 | Dustin Carstens | Yes | Document Requirement |  | 1 | 2025-10-07 | 2025-10-08 | 25 | bar: 2025-10-07 to 2025-10-08
| 1 | 2 | 1.2.7 | Dustin Carstens | Yes | Create Requirements Traceability Matrix |  | 1 | 2025-10-07 | 2025-10-08 | 0 | bar: 2025-10-07 to 2025-10-08
| 1 | 2 | 1.2.8 | Dustin Carstens | Yes | Finalize Project Plan |  | 1 | 2025-10-10 | 2025-10-11 | 75 | bar: 2025-10-10 to 2025-10-11
| 1 | 3 | 1.3 |  |  | Monitoring and Controlling Phase | Tracking and Control Activities
| 1 | 3 | 1.3.1 | Dustin Carstens | No | Track Project Progress |  | 18 | 2025-10-06 | 2025-10-24 | 100
| 1 | 3 | 1.3.2 | Dustin Carstens | No | Update Risk Register |  | 18 | 2025-10-06 | 2025-10-24 | 100
| 1 | 3 | 1.3.3 | Dustin Carstens | No | Manage Issues and Change |  | 18 | 2025-10-06 | 2025-10-24 | 100
| 1 | 3 | 1.3.4 | Dustin Carstens | No | Conduct Weekly Status Review |  | 18 | 2025-10-06 | 2025-10-24 | 100
| 1 | 4 | 1.4 |  |  | Closing Phase | Project Closeout Activities
| 1 | 4 | 1.4.1 | Dustin Carstens | Yes | Create Final Project Report |  | 1 | 2025-10-23 | 2025-10-24 | 80 | bar: 2025-10-23 to 2025-10-24
| 1 | 4 | 1.4.2 | Dustin Carstens | No | Document Lessons Learned |  | 18 | 2025-10-06 | 2025-10-24 | 0
| 1 | 4 | 1.4.3 | Dustin Carstens | Yes | Archive Project Documentation |  | 1 | 2025-10-23 | 2025-10-24 | 0 | bar: 2025-10-23 to 2025-10-24
| 2 | 0 | 2 |  |  | Design and Planning | Design and Architecture Work
| 2 | 1 | 2.1 |  |  | Requirements Gathering | Understand Needs and Goals
| 2 | 1 | 2.1.1 | Dustin Carstens | Yes | Define Website Purpose and Goals |  | 1 | 2025-10-07 | 2025-10-08 | 100 | bar: 2025-10-07 to 2025-10-08
| 2 | 1 | 2.1.2 | Dustin Carstens | Yes | Indentify Target Audience Needs |  | 0 | 2025-10-07 | 2025-10-07 | 100 | bar: 2025-10-07
| 2 | 1 | 2.1.3 | Dustin Carstens | Yes | Define Success Metrics |  | 1 | 2025-10-08 | 2025-10-09 | 100 | bar: 2025-10-08 to 2025-10-09
| 2 | 2 | 2.2 |  |  | Design Wireframes | Single-Page Layout Planning
| 2 | 2 | 2.2.1 | Dustin Carstens | Yes | Sketch Section Layout |  | 2 | 2025-10-12 | 2025-10-14 | 100 | bar: 2025-10-12 to 2025-10-14
| 2 | 2 | 2.2.2 | Dustin Carstens | No | Sketch About Section Layout |  | 2 | 2025-10-12 | 2025-10-14 | 100 | bar: 2025-10-12 to 2025-10-14
| 2 | 2 | 2.2.3 | Dustin Carstens | No | Sketch Project Section Layout |  | 2 | 2025-10-12 | 2025-10-14 | 100 | bar: 2025-10-12 to 2025-10-14
| 2 | 2 | 2.2.4 | Dustin Carstens | No | Sketch Resume Section Layout |  | 2 | 2025-10-12 | 2025-10-14 | 100 | bar: 2025-10-12 to 2025-10-14
| 2 | 2 | 2.2.5 | Dustin Carstens | No | Sketch Contact Section Layout |  | 2 | 2025-10-12 | 2025-10-14 | 100 | bar: 2025-10-12 to 2025-10-14
| 2 | 2 | 2.2.6 | Dustin Carstens | Yes | Create Navigation Structure |  | 1 | 2025-10-15 | 2025-10-16 | 100 | bar: 2025-10-15 to 2025-10-16
| 2 | 2 | 2.2.7 | Dustin Carstens | Yes | Design Section Transitions/Animations |  | 1 | 2025-10-15 | 2025-10-16 | 100 | bar: 2025-10-15 to 2025-10-16
| 2 | 3 | 2.3 |  |  | Visual Design | Brand and Aesthetics
| 2 | 3 | 2.3.1 | Dustin Carstens | Yes | Select Colors for Site |  | 1 | 2025-10-15 | 2025-10-16 | 100 | bar: 2025-10-15 to 2025-10-16
| 2 | 3 | 2.3.2 | Dustin Carstens | Yes | Choose Typography |  | 1 | 2025-10-15 | 2025-10-16 | 100 | bar: 2025-10-15 to 2025-10-16
| 2 | 4 | 2.4 |  |  | Technical Architecture | Single-Page Architecture Planning
| 2 | 4 | 2.4.1 | Dustin Carstens | 2.4.1 | Select Technology Stack |  | 1 | 2025-10-17 | 2025-10-18 | 100 | bar: 2025-10-17 to 2025-10-18
| 2 | 4 | 2.4.2 | Dustin Carstens | 2.4.2 | Plan File Structure |  | 1 | 2025-10-17 | 2025-10-18 | 100 | bar: 2025-10-17 to 2025-10-18
| 2 | 4 | 2.4.3 | Dustin Carstens | 2.4.3 | Set Up Development Environment |  | 1 | 2025-10-17 | 2025-10-18 | 100 | bar: 2025-10-17 to 2025-10-18
| 3 | 0 | 3 |  |  | Development | All Coding and Content Work
| 3 | 1 | 3.1 |  |  | Environment Setup | Dev Environment Preparation
| 3 | 1 | 3.1.1 | Dustin Carstens | Yes | Install VS Code and Extension |  | 1 | 2025-10-17 | 2025-10-18 | 100 | bar: 2025-10-17 to 2025-10-18
| 3 | 1 | 3.1.2 | Dustin Carstens | Yes | Set Up GitHub and GitHub Repository |  | 1 | 2025-10-17 | 2025-10-18 | 100 | bar: 2025-10-17 to 2025-10-18
| 3 | 1 | 3.1.3 | Dustin Carstens | Yes | Configure Local Development Environment |  | 1 | 2025-10-17 | 2025-10-18 | 100 | bar: 2025-10-17 to 2025-10-18
| 3 | 1 | 3.1.4 | Dustin Carstens | Yes | Create Project Folder Structure |  | 1 | 2025-10-17 | 2025-10-18 | 100 | bar: 2025-10-17 to 2025-10-18
| 3 | 2 | 3.2 |  |  | Create Website Structure | Single HTML File With Sections
| 3 | 2 | 3.2.1 | Dustin Carstens | Yes | Create HTML Index File |  | 1 | 2025-10-17 | 2025-10-18 | 100 | bar: 2025-10-17 to 2025-10-18
| 3 | 2 | 3.2.2 | Dustin Carstens | Yes | Set Up HTML Header (Meta Tags, Title, Links) |  | 1 | 2025-10-17 | 2025-10-18 | 100 | bar: 2025-10-17 to 2025-10-18
| 3 | 2 | 3.2.3 | Dustin Carstens | Yes | Create the different section containers |  | 1 | 2025-10-17 | 2025-10-18 | 100 | bar: 2025-10-17 to 2025-10-18
| 3 | 2 | 3.2.4 | Dustin Carstens | Yes | Create Footer Element |  | 1 | 2025-10-17 | 2025-10-18 | 100 | bar: 2025-10-17 to 2025-10-18
| 3 | 3 | 3.3 |  |  | Navigation Development | Anchor Link Navigation System
| 3 | 3 | 3.3.1 | Dustin Carstens | Yes | Create Fixed/Sticky Navigation Bar |  | 1 | 2025-10-17 | 2025-10-18 | 100 | bar: 2025-10-17 to 2025-10-18
| 3 | 3 | 3.3.2 | Dustin Carstens | Yes | Add Navigation Links (Anchor Links to Sections) |  | 1 | 2025-10-17 | 2025-10-18 | 100 | bar: 2025-10-17 to 2025-10-18
| 3 | 3 | 3.3.3 | Dustin Carstens | No | Style Navigation Menu |  | 0 | 2025-10-19 | 2025-10-19 | 100 | bar: 2025-10-19
| 3 | 3 | 3.3.4 | Dustin Carstens | Yes | Implement Smooth Scroll Behavior (Java Script) |  | 0 | 2025-10-19 | 2025-10-19 | 100 | bar: 2025-10-19
| 3 | 3 | 3.3.5 | Dustin Carstens | No | Add Active Section Highlighting |  | 0 | 2025-10-19 | 2025-10-19 | 100 | bar: 2025-10-19
| 3 | 3 | 3.3.6 | Dustin Carstens | Yes | Create Mobile Navigation Menu |  | 0 | 2025-10-19 | 2025-10-19 | 100 | bar: 2025-10-19
| 3 | 4 | 3.4 |  |  | Globl Styles and Framework | CSS Foundation for Entire Page
| 3 | 4 | 3.4.1 | Dustin Carstens | No | Create Global CSS Reset/Normalize |  | 0 | 2025-10-19 | 2025-10-19 | 100 | bar: 2025-10-19
| 3 | 4 | 3.4.2 | Dustin Carstens | Yes | Define CSS Variables |  | 0 | 2025-10-19 | 2025-10-19 | 100 | bar: 2025-10-19
| 3 | 4 | 3.4.3 | Dustin Carstens | Yes | Create Reponsive Grid System |  | 0 | 2025-10-19 | 2025-10-19 | 100 | bar: 2025-10-19
| 3 | 4 | 3.4.4 | Dustin Carstens | No | Style Typography |  | 0 | 2025-10-19 | 2025-10-19 | 100 | bar: 2025-10-19
| 3 | 4 | 3.4.5 | Dustin Carstens | No | Create Reusable Component Style |  | 0 | 2025-10-19 | 2025-10-19 | 100 | bar: 2025-10-19
| 3 | 5 | 3.5 |  |  | Section Development | Build all 5 Sections with index.html
| 3 | 5 | 3.5.1 | Dustin Carstens | Yes | Develop Home Section |  | 0 | 2025-10-19 | 2025-10-19 | 100 | bar: 2025-10-19
| 3 | 5 | 3.5.2 | Dustin Carstens | Yes | Develop About Section |  | 0 | 2025-10-19 | 2025-10-19 | 100 | bar: 2025-10-19
| 3 | 5 | 3.5.3 | Dustin Carstens | Yes | Develop Projects Section |  | 0 | 2025-10-19 | 2025-10-19 | 100 | bar: 2025-10-19
| 3 | 5 | 3.5.4 | Dustin Carstens | Yes | Develop Resume Section |  | 0 | 2025-10-19 | 2025-10-19 | 100 | bar: 2025-10-19
| 3 | 5 | 3.5.5 | Dustin Carstens | Yes | Develop Contact Section |  | 0 | 2025-10-19 | 2025-10-19 | 100 | bar: 2025-10-19
| 3 | 6 | 3.6 |  |  | Content Integration | Add all content to sections
| 3 | 6 | 3.6.1 | Dustin Carstens | Yes | Write and Add Home Section Content |  | 0 | 2025-10-19 | 2025-10-19 | 100 | bar: 2025-10-19
| 3 | 6 | 3.6.2 | Dustin Carstens | Yes | Write and Add Section Content |  | 0 | 2025-10-19 | 2025-10-19 | 100 | bar: 2025-10-19
| 3 | 6 | 3.6.3 | Dustin Carstens | Yes | Prepare and Add Project Descriptions |  | 0 | 2025-10-19 | 2025-10-19 | 15 | bar: 2025-10-19
| 3 | 6 | 3.6.4 | Dustin Carstens | Yes | Add Resume Content |  | 1 | 2025-10-20 | 2025-10-21 | 100 | bar: 2025-10-20 to 2025-10-21
| 3 | 6 | 3.6.5 | Dustin Carstens | Yes | Upload Images |  | 1 | 2025-10-20 | 2025-10-21 | 100 | bar: 2025-10-20 to 2025-10-21
| 3 | 6 | 3.6.6 | Dustin Carstens | Yes | Create PM Documentation Page |  | 1 | 2025-10-20 | 2025-10-21 | 0 | bar: 2025-10-20 to 2025-10-21
| 4 | 0 | 4 |  |  | Testing and Quality Assurance | All Testing Activities
| 4 | 1 | 4.1 |  |  | Functional Testing | Test Navigation and Features
| 4 | 1 | 4.1.1 | Dustin Carstens | Yes | Test Navigation Links |  | 1 | 2025-10-20 | 2025-10-21 | 100 | bar: 2025-10-20 to 2025-10-21
| 4 | 1 | 4.1.2 | Dustin Carstens | Yes | Test Smooth Scroll Behavior |  | 1 | 2025-10-20 | 2025-10-21 | 100 | bar: 2025-10-20 to 2025-10-21
| 4 | 1 | 4.1.3 | Dustin Carstens | Yes | Test Section Functionality |  | 1 | 2025-10-20 | 2025-10-21 | 100 | bar: 2025-10-20 to 2025-10-21
| 4 | 1 | 4.1.4 | Dustin Carstens | Yes | Test Resume Link Button |  | 1 | 2025-10-20 | 2025-10-21 | 100 | bar: 2025-10-20 to 2025-10-21
| 4 | 1 | 4.1.5 | Dustin Carstens | Yes | Test All interactive Elements |  | 1 | 2025-10-20 | 2025-10-21 | 100 | bar: 2025-10-20 to 2025-10-21
| 4 | 1 | 4.1.6 | Dustin Carstens | Yes | Test Section Transitions |  | 1 | 2025-10-20 | 2025-10-21 | 100 | bar: 2025-10-20 to 2025-10-21
| 4 | 1 | 4.1.7 | Dustin Carstens | Yes | Verify All Content Displays Correct |  | 1 | 2025-10-20 | 2025-10-21 | 100 | bar: 2025-10-20 to 2025-10-21
| 4 | 2 | 4.2 |  |  | Cross Browser Testing | Browser Compatibility Test
| 4 | 2 | 4.2.1 | Dustin Carstens | No | Test in Chrome |  | 1 | 2025-10-20 | 2025-10-21 | 100 | bar: 2025-10-20 to 2025-10-21
| 4 | 2 | 4.2.2 | Dustin Carstens | No | Test in FireFox |  | 1 | 2025-10-20 | 2025-10-21 | 0 | bar: 2025-10-20 to 2025-10-21
| 4 | 2 | 4.2.3 | Dustin Carstens | No | Test in Edge |  | 1 | 2025-10-20 | 2025-10-21 | 0 | bar: 2025-10-20 to 2025-10-21
| 4 | 3 | 4.3 |  | 4.3 | Content Quality Review | Proofing and Content Cheks
| 4 | 3 | 4.3.1 | Dustin Carstens | No | Proofread All Text Content |  | 1 | 2025-10-21 | 2025-10-22 | 100 | bar: 2025-10-21 to 2025-10-22
| 4 | 3 | 4.3.2 | Dustin Carstens | No | Check Grammer |  | 1 | 2025-10-21 | 2025-10-22 | 100 | bar: 2025-10-21 to 2025-10-22
| 4 | 3 | 4.3.3 | Dustin Carstens | Yes | Verfiy All External Links Work |  | 1 | 2025-10-21 | 2025-10-22 | 100 | bar: 2025-10-21 to 2025-10-22
| 4 | 3 | 4.3.4 | Dustin Carstens | Yes | Verify Project Documents Open Correctly |  | 1 | 2025-10-21 | 2025-10-22 | 100 | bar: 2025-10-21 to 2025-10-22
| 4 | 4 | 4.4 | Dustin Carstens | No | User Acceptance Testing | Final Approval Testing |  |  |  | 100
| 4 | 4 | 4.4.1 | Dustin Carstens | Yes | Self-Review Against Acceptance Criteria |  | 1 | 2025-10-21 | 2025-10-22 | 100 | bar: 2025-10-21 to 2025-10-22
| 4 | 4 | 4.4.2 | Dustin Carstens | Yes | Test User Experience |  | 1 | 2025-10-21 | 2025-10-22 | 100 | bar: 2025-10-21 to 2025-10-22
| 4 | 4 | 4.4.3 | Dustin Carstens | Yes | Request Mentor Feedback |  | 1 | 2025-10-21 | 2025-10-22 | 25 | bar: 2025-10-21 to 2025-10-22
| 4 | 4 | 4.4.4 | Dustin Carstens | Yes | Final PM Approval |  | 0 | 2025-10-23 | 2025-10-23 | 100 | bar: 2025-10-23
| 5 | 0 | 5 |  |  | Deployment and Launch | Go-Live Activities
| 5 | 1 | 5.1 |  |  | Pre-Launch Preparation | Deployment Setup
| 5 | 1 | 5.1.1 | Dustin Carstens | Yes | Create GitHub Pages and Branch |  | 1 | 2025-10-21 | 2025-10-22 | 100 | bar: 2025-10-21 to 2025-10-22
| 5 | 1 | 5.1.2 | Dustin Carstens | Yes | Set Up HTTPS/SSL |  | 1 | 2025-10-21 | 2025-10-22 | 100 | bar: 2025-10-21 to 2025-10-22
| 5 | 1 | 5.1.3 | Dustin Carstens | Yes | Configure GitHub Pages Settings |  | 1 | 2025-10-21 | 2025-10-22 | 100 | bar: 2025-10-21 to 2025-10-22
| 5 | 1 | 5.1.4 | Dustin Carstens | Yes | Verify index.html is Root File |  | 1 | 2025-10-21 | 2025-10-22 | 100 | bar: 2025-10-21 to 2025-10-22
| 5 | 1 | 5.1.5 | Dustin Carstens | Yes | Create Backup of Final Version |  | 1 | 2025-10-21 | 2025-10-22 | 0 | bar: 2025-10-21 to 2025-10-22
| 5 | 2 | 5.2 |  |  | Deployment | Make Site Live
| 5 | 2 | 5.2.1 | Yes | Yes | Push Code to GitHub Repository |  | 1 | 2025-10-21 | 2025-10-22 | 100 | bar: 2025-10-21 to 2025-10-22
| 5 | 2 | 5.2.2 | Yes | Yes | Enable GitHub Pages |  | 1 | 2025-10-22 | 2025-10-23 | 100 | bar: 2025-10-22 to 2025-10-23
| 5 | 2 | 5.2.3 | Yes | Yes | Verify Live Site Loads Correctly |  | 1 | 2025-10-22 | 2025-10-23 | 100 | bar: 2025-10-22 to 2025-10-23
| 5 | 2 | 5.2.4 | Yes | Yes | Test All Sections on Live Site |  | 1 | 2025-10-22 | 2025-10-23 | 100 | bar: 2025-10-22 to 2025-10-23
| 5 | 2 | 5.2.5 | Yes | Yes | Test Navigation on Live Site |  | 1 | 2025-10-22 | 2025-10-23 | 100 | bar: 2025-10-22 to 2025-10-23
| 5 | 3 | 5.3 |  |  | Launch Communications | Announce and Share
| 5 | 3 | 5.3.1 | No | No | Update LinkedIn Profile With Portfolio Link |  | 0 | 2025-10-24 | 2025-10-24 | 100 | bar: 2025-10-24; 2025-10-26
| 5 | 3 | 5.3.2 | No | No | Update Resume with Portfolio Link |  | 0 | 2025-10-24 | 2025-10-24 | 100 | bar: 2025-10-24; 2025-10-26
| 5 | 3 | 5.3.3 | No | No | Share in Professional Network |  | 0 | 2025-10-24 | 2025-10-24 | 100 | bar: 2025-10-24; 2025-10-26
| 5 | 3 | 5.3.4 | No | No | Document Launch Date and Initial Metrics |  | 0 | 2025-10-24 | 2025-10-24 | 100 | bar: 2025-10-24; 2025-10-26
| 5 | 4 | 5.4 |  |  | Post-Launch Support | Monitor and Maintain
| 5 | 4 | 5.4.1 | No | No | Monitor Site Performance |  | 0 | 2025-10-24 | 2025-10-24 | 0 | bar: 2025-10-24; 2025-10-26
| 5 | 4 | 5.4.2 | No | No | Track Analytics |  | 0 | 2025-10-24 | 2025-10-24 | 0 | bar: 2025-10-24; 2025-10-26
| 5 | 4 | 5.4.3 | No | No | Address Any Issues Found |  | 0 | 2025-10-24 | 2025-10-24 | 0 | bar: 2025-10-24; 2025-10-26
| 5 | 4 | 5.4.4 | No | No | Plan Future Updates |  | 0 | 2025-10-24 | 2025-10-24 | 0 | bar: 2025-10-24; 2025-10-26

## Stakeholder Register
Back to Table of Contents
Stakeholder Register
Planning Phase - Stakeholder Analysis
| Initiation Phase - Complete After Project Charter | [8 empty] | Current Attitude | [5 empty] | Desired Attitude
| SID | Stakeholder's Name | Role | Contact Information | Engagement Strategy | Location | Requirements/Expectations | Power/Influence (1-5) | Interest/Impact (1-5) | Leading | Unaware | Resistant | Cautious | Neutral | Supportive | Leading | Unaware | Resistant | Cautious | Neutral | Supportive | Stakeholder Classification | Notes
| S-001 | Dustin Carstens | Project Manager | Email | Email | On-Site | 1.) Create PM Methodology Demonstration 2.) Create Functional Portfolio, 3.) Role Advancement Tool | 5 | 5 | Leading | [5 empty] | Leading | [5 empty] | Interal, Primary
| S-002 | Prospective Employers | Hiring Manager | LinkedIn | LinkedIn | Off-site | 1.) Reviews and Evaluates Website 2.) Able to Navigate Website Easy 3.) Evaluates Disciplinary Projects | 4 | 4 | Unaware | [5 empty] | Supportive | [5 empty] | External, Primary
| S-003 | Current Professional Network | Mentor/Peer | LinkedIn | Email | Off-site | 1.) Reviews Website 2.) Able to Navigate Website Easily | 2 | 2 | Neutral | [5 empty] | Supportive | [5 empty] | External, Secondary
| S-004 | Website Visitors | General Public | Website Contact | Website | Off-site | 1.) Able to Navigate Website Easily | 1 | 1 | Unaware | [5 empty] | Neutral | [5 empty] | External, Tertiary
| S-005 | GitHub | Hosting Platform | Support Portal | Support Portal | Off-Site | 1.) Actively Supports Web Domain | 2 | 2 | Supportive | [5 empty] | Supportive | [5 empty] | External, Tertiary

## Risk Register
Back to Table of Contents
Risk Register
| Initial Risk Assessment | [9 empty] | Threat Response Strategy
[5 empty] | Objectives Impacted by Risk | Scope | Probability Scale |  | Impact Scale |  | Risk Score |  | For Threats
[6 empty] | Schedule | 5 | Very High | 3 | High | 9-15 | High | Response Techniques
[6 empty] | Budget | 4 | High | 2 | Medium | 4-8 | Medium | Avoid the Threat
[6 empty] | Completion | 3 | Medium | 1 | Low | 1-3 | Low | Transfer the Threat
[6 empty] | Technical | 2 | Low |  |  |  |  | Mitigate the Threat
[6 empty] | Quality | 1 | Very Low |  |  |  |  | Accept the Threat
| Risk ID | WBS Reference | Risk Category | Risk Description | Risk Owner |  | Probability |  | Impact |  | Risk Matrix Score |  | Priority | Risk Reponse Strategy | Response Actions | Related Assumption/Constraint | Status | Trigger Conditions | Date Identified | Notes
|  |  | r | r
| R-001 | 3.5, 3.7 | Technical | Techincal Requirements exceed present ability of project manager; skills gap in HTML/CSS/ JavaScript development | Dustin Carstens |  | 3 |  | 4 |  | 12 | High | High | Mitigate the Threat | Leverage A.I models in absence of expertise | A-002, C-003 | Active | Struggle to develop the necessary components for website | 2025-10-06 | Have basic HTML knowledge, Javascript is weakest area
| R-002 | 1.2 | Schedule | Ambiguous project management domain knowledge could impact timelines; unfamiliarity with PM artifacts may slow documentation | Dustin Carstens |  | 3 |  | 3 |  | 9 | High | High | Mitigate the Threat | Use PMBOK as a reference tool and search engine for assistance in idea generation. | C-003 | Active | Taking longer than 1 week to complete planning artifacts; confusion about artifact requirements | 2025-10-06 | Creating artifacts as learning exercise; may need iterations
| R-003 | 2.4, 3.1 | Budget | Unforseen technological need causes budget to expand greater than $20; unexpected cost for tools, domain, or services | Dustin Carstens |  | 2 |  | 3 |  | 6 | Medium | Medium | Accept/Mitigate | Use only verified free tools, research all tools before comitting to use | C-001, C-005 | Active | Discovering needed feature requires paid tool; free hosting limits exceeded domain cost required | 2025-10-09 | $0 spent to date; $20 dollar buffer available
| R-004 | 5.1, 5.2 | Technical | Github Pages platform discontinued, modified, or free tier eliminated | Dustin Carstens |  | 1 |  | 5 |  | 5 | Medium | Medium | Mitigate the Threat | Find alternative for hosting website domain and code. | A-001 | Active | Github announces removal of their free domain hosting feature | 2025-10-09 | Low Probability that GitHub makes changes to their domain hosting.
| R-005 | 3.0, 4.0 | Resources | Internet Connectivity disruptions prevents work on project. Home Wifi outage or ISP issues | Dustin Carstens |  | 2 |  | 3 |  | 6 | Medium | Medium | Mitigate the Threat | Calll ISP and request assistance, utilize hotspot until wifi is back online | A-004 | Active | Home internet down for longer than 30 minutes | 2025-10-09 | Service has been uninterrupted for two years
| R-006 | 3.0,4.0 | Schedule | Insufficient time available for project; work-life balance challenges lead to reduced productivity | Dustin Carstens |  | 3 |  | 4 |  | 12 | High | High | Mitigate the Threat | Commit to realistic time period of 10-15 hours a week. Block dedicated time to work on project | A-008, C-002, C-004 | Active | Consistently working less than 8 hours a week on the project | 2025-10-09 | Primary employment take priority.
| R-007 | 3.7, 4.2 ,4.3 | Quality | Website fails browser cross compatability testing; functions and looks poorly on mobile device | Dustin Carstens |  | 3 |  | 3 |  | 9 | High | High | Mitigate the Threat | Debug throughout design process to mitigate cross compatability issues. Resolving issues as they arise. | C-003 | Active | Layout breaks on mobile device. Website doesn't load on main browsers. | 2025-10-09 | Will test on 3 browsers and 2 mobile devices
| R-008 | 2.2, 3.5, 3.7 | Scope | Scope creep from adding unnecessary features | Dustin Carstens |  | 4 |  | 3 |  | 12 | High | High | Avoid the Threat | Document clear scope in project scope | A-007 | Active | Adding features not in original scope. | 2025-10-09 | Risk of overengineering due to enthusiasm
| R-009 | 4.6 | Stakeholder | Professional Network unavailable for feedback | Dustin Carstens |  | 2 |  | 2 |  | 4 | Medium | Medium | Accept the Threat | Give notice in advance to mentors and share during 1:1 meetings | A-005 | Active | Mentors have consistent unavailability | 2025-10-09 | Schedule time to meet with 3+ mentors
| R-010 | 3.4, 4.5 | Quality | Content errors, typos, grammar issues, broken links. Potential to damage professional credibility | Dustin Carstens |  | 3 |  | 4 |  | 12 | High | High | Mitigate the Threat | Click on links, run content through spell check. |  | Active | Finding multiple errors during review, links not functioning as intended. | 2025-10-09 | High visibility, mistakes can commnicate the opposite of project vision.
| R-011 | 3.1, 3.2, 3.3, 3.4, 3.5, 3.6, 3.7, 3.8 | Technical | Version Control issues; code loss due to inadequate backup | Dustin Carstens |  | 2 |  | 4 |  | 8 | Medium | Medium | Mitigate the Threat | Use GitHub for all code changes. Maintain local backup |  | Active | Accidental file deletion on hard drive. Corrupted file. | 2025-10-09 | Code stored in a variety of places
| R-012 | 2.0, 3.0, 5.3 | Stakeholder | Mentors unimpressed with outputs | Dustin Carstens |  | 3 |  | 5 |  | 15 | High | High | Mitigate the Threat | Follow Project scope and ensure 100% quality in product delivery |  | Active | Receive negative feedback on discipline tangibles and website | 2025-10-09 | Primary Goal
| R-013 | 3.2, 3.3, 3.4, 3.5 | Schedule | Dependencies between task cause cascading delays: Critical path blocked | Dustin Carstens |  | 3 |  | 3 |  | 9 | High | High | Mitigate the Threat | Utilize response actions from the risk register to actively resolve threats blocking critical path |  | Active | Critical path blocked, deliverable needs completed before other parts of project can be started | 2025-10-09 | Only individual working on project so bottleneck will be easily identifiable

## Assumption Log
Back to Table of Contents
Assumption Log
| Planing Phase - Complete After Project Charter |  |  |  |  | Impact Level
| A-ID | Type | Category | Description | Impact if False | Low | Medium | High | Affected Areas | Status | Validation Method | Owner | Related Risk | Date Identified | Notes
| A-001 | Assumption | Technical | GitHub Pages will remain free and available throughout the project | Would need to find alternative hosting, potential cost increase | High |  |  | Cost, Schedule | Active | GitHub Announcements | Dustin Carstens | R-004 | 2025-10-06 | Free tier sufficient for portfolio site
| A-002 | Assumption | Resources | Required web development skills can be learned through free online resources. | May need to increase cost to account for additional instructional material | Medium |  |  | Cost, Schedule | Active | Find web design solutions on the internet | Dustin Carstens | R-001 | 2025-10-06 | Claude AI, Google Gemini, GitHub examples.
| A-003 | Assumption | Resources | Current hardware is sufficient for project | May need to purchase new equipment, budget impact | High |  |  | Cost, Schedule | Validated | Test VS Code performace with throughout project. | Dustin Carstens | R-011 | 2025-10-06 | Validated: Laptop runs code in VS code 10/09/2025
| A-004 | Assumption | Technical | Internet connectivity will remain consistently available. | Cannot work on project; schedule delays | High |  |  | Schedule | Validated | Search on google browser to verify working internet | Dustin Carstens | R-005 | 2025-10-06 | Validated: Internet is functional as of 10/06/2025
| A-005 | Assumption | Stakeholder | Professional network will be available for feedback when requested | Limited feedback on effectiveness of portfolio | Low |  |  | Quality | Active | Verify with 3 mentors that they were able to review the portfolio | Dustin Carstens | R-009 | 2025-10-06 | Plan to request feedback one week after launch.
| A-006 | Assumption | Technical | VS Code and Git are sufficient development tools | May need additional paid tools | Low |  |  | Cost | Validated | Complete setup and test basic workflow | Dustin Carstens | R-001, R-011 | 2025-10-06 | Validated: Tool installed and working 10/802025
| A-007 | Assumption | Scope | Five Pages (Home, About, Projects, Resume, Contact) are sufficient to meet stakeholder needs | May need additional pages, scope creep. | Medium |  |  | Scope, Schedule | Active | Validate with Wireframe review | Dustin Carstens | R-008, R-012 | 2025-10-06 | To be validated during design phase
| A-008 | Assumption | Schedule | Can dedicate 10-15 hours per week to project | Project timeline extends; miss launch date | High |  |  | Schedule | Active | Track actual hours weekly; adjust schedule as needed | Dustin Carstens | R-006 | 2025-10-06 | Based on current work/life commitments
| A-009 | Assumption | Quality | Three sample projects are sufficient to demonstrate capabilities | Employers may want to see more work; reduced competitiveness | Medium |  |  | Scope, Quality | Active | Ask mentor feedback | Dustin Carstens | R-012 | 2025-10-06 | May increase to 5 projects if needed.
| C-001 | Constraint | Budget | Project budget to be limited to $20 maximum | Additional fund will need to be approved from sponsor | High |  |  | Cost | Active | Track expenditures in budget log | Dustin Carstens | R-003 | 2025-10-06 | $0 spend to date.
| C-002 | Constraint | Resources | Single-Person team (all roles performed by PM) | All work dependent on one person's availability and skills | High |  |  | Schedule, Resources | Active | Manage workload carefully; avoid burnout | Dustin Carstens | R-006, R-013 | 2025-10-06 | No option to delegate task
| C-003 | Constraint | Knowledge | Limited formal web development training | Learning curve may slow progress | Medium |  |  | Schedule, Quality | Active | Allocating time for troubleshooting, use quality resources | Dustin Carstens | R-001, R-007 | 2025-10-06 | Have Basic HTML/ CSS knowledge
| C-004 | Constraint | Time | Must work outside primary employment hours | Limits available project time; affects schedule | High |  |  | Schedule | Active | Maintain work life balance; realistic scheduling. | Dustin Carstens | R-006 | 2025-10-06 | Evenings and weekends only.
| C-005 | Constraint | Technical | Must use free/open-source tools only | Limits functionality | Medium |  |  | Quality, Scope | Active | Research free alternatives before comitting to features | Dustin Carstens | R-003, R-007, R-014 | 2025-10-06 | Aligned with zero budget goals

## Requirements
Back to Table of Contents
Explanation: This is what is needed for the project to be completed. The WBS is how to build it.
Requirements
| ID | Requirement | Must Have | How to Verify | WBS | Status |  |  |  | Progress Percent %
[6 empty] | Not Started | In Progress | Complete | Deferred
| R-01 | Home section with name and professional intro | Yes | Section visible with name tagline and summary | 3.5.1 | Complete |  |  |  | 100
| R-02 | About with section with populated information | Yes | Relevant data displayed in about section | 3.5.2 | Complete |  |  |  | 100
| R-03 | Projects section showing 3+ completed projects | Yes | Minimum 3 projects with title description image | 3.5.3 | Complete |  |  |  | 66
| R-04 | PM documentation artifacts downloadable | Yes | 6+ PM docs (Charter WBS Schedule etc) | 3.6.7 | Complete |  |  |  | 100
| R-05 | Resume section with experience and education | Yes | Work history education and skills displayed | 3.5.4 | Complete |  |  |  | 100
| R-06 | Email displayed on contact section | Yes | Email is viewable | 3.5.5 | Complete |  |  |  | 100
| R-07 | Downloadable resume PDF | Yes | Resume downloads as PDF under 2MB | 3.6.6 | Complete |  |  |  | 100
| R-08 | Fixed navigation menu (Home About Projects Resume Contact) | Yes | Nav bar stays visible; links to all 5 sections | 3.3.1 | Complete |  |  |  | 100
| R-09 | Smooth scroll between sections | Yes | Clicking nav smoothly scrolls (not jumps) | 3.3.4 | Complete |  |  |  | 100
| R-10 | Mobile hamburger menu | Yes | Nav becomes hamburger menu on phones | 3.3.6 | Complete |  |  |  | 100
| R-11 | Page loads in under 3 seconds | Yes | Google Lighthouse shows load time <3 seconds | 4.4.1 | Complete |  |  |  | 100
| R-12 | Works in Chrome Firefox Safari | Yes | Tested and functional in all 3 browsers | 4.2. | Complete |  |  |  | 100
| R-13 | Mobile responsive (works on all screen sizes) | Yes | Displays properly on phones tablets desktops | 4.3. | Complete |  |  |  | 100
| R-14 | HTTPS secure connection | Yes | Site URL shows https:// | 5.1.3 | Complete |  |  |  | 100
| R-15 | All links work (no broken links) | Yes | 100% of links functional; no 404 errors | 4.5.3 | Complete |  |  |  | 100
| R-16 | Zero spelling and grammar errors | Yes | Content proofread with Grammarly | 4.5.1 | Complete |  |  |  | 100
| R-17 | Hosted on GitHub Pages (free) | Yes | Site live on GitHub Pages | 5.2. | Complete |  |  |  | 100
| R-18 | Single HTML file (single-page site) | Yes | All sections in one index html | 2.4.1 | Complete |  |  |  | 100
| R-19 | Git version control | Yes | Code in GitHub repository | 3.1.2 | Complete |  |  |  | 100
| R-20 | Professional appearance | Yes | Clean modern design; mentor approves | 4.6.3 | Complete |  |  |  | 100
| R-21 | Budget stays under $20 | Yes | Track all expenses; total ≤ $20 |  | Complete |  |  |  | 100